## Read Me
ShiftQuality Pro
Communication Plan for Releases
Plan every message a release needs — who hears what, through which channel, and when — so nobody is surprised and nothing gets forgotten.
How to use it:
1. Fill the release header (name, date, owner) on the 'Plan' tab.
2. One row per communication. Work the audiences top to bottom.
3. Set Status as you go: Draft / Reviewed / Sent.
4. See the 'Lead times' tab for how far ahead to send each kind.
ShiftQuality — real knowledge for builders. shiftquality.com

## Plan
Communication Plan
Release:
Release date:
Owner:
Audience | Message | Channel | Timing | Owner | Status
API integrators | Breaking change + migration guide | Email + docs | T-14d | PM | Draft
All customers | What's changing and when | Email | T-7d | PM | Draft
Support team | What to expect + FAQ | Slack + doc | T-3d | Lead | Draft
Internal eng | Release plan + freeze window | Slack | T-1d | Owner | Draft
On-call | Heads-up + rollback plan | Calendar + DM | T-1d | Owner | Draft
Customers (live) | Status during rollout | Status page | T-0 → T+2h | SRE | Draft

## Lead times
How far ahead to communicate
Kind of change | Lead time
Major breaking changes | 90 days
Significant user-visible changes | 14–30 days
Maintenance windows | 7–14 days
Emergency / live status | Same day