## Read Me
ShiftQuality Pro
Risk Register
Name the handful of things that could genuinely derail the project — each with a real owner and a real mitigation — and prune it every week. An unmaintained register is worse than none: it launders 'we stopped thinking about risk' into 'we have a process.'
How to use it:
1. One row per risk on the 'Register' tab. Give each a stable ID (R1, R2 ...).
2. Set Likelihood and Impact (High/Medium/Low) — Score fills in automatically (L×I, H=3/M=2/L=1).
3. Every risk gets a single named Owner and a real Mitigation — not 'monitor closely.'
4. Update Status as risks move: Open → Mitigated → Closed (or Realized if it happened).
5. Review weekly for top-score risks; prune stale rows. See the 'Reference' tab for scoring + strategies.
Keep it short and alive. A register that's all 'Open' for two months is one nobody's maintaining.
ShiftQuality — real knowledge for builders. shiftquality.com

## Register
Risk Register
ID | Risk | Category | Likelihood | Impact | Score | Status | Mitigation | Owner | Updated

## Reference
Scoring, Status & Strategies
Score = Likelihood × Impact
High / Med / Low | Numeric values 3 / 2 / 1.
9 (H×H) | Top priority — act now.
6 (H×M / M×H) | Serious — active mitigation.
3–4 | Aware; mitigate or monitor.
1 (L×L) | Bottom priority — likely accept.
Status lifecycle
Open | Active concern, mitigation in progress.
Mitigated | Mitigation in place, residual risk lower.
Closed | No longer a concern (passed, prevented, irrelevant).
Realized | The bad thing happened — it's now an issue, not a risk.
Mitigation strategies
Avoid | Restructure so the risk is impossible.
Reduce | Lower the likelihood or the impact.
Transfer | Make it someone else's problem (vendor, insurance, contract).
Accept | Acknowledge but don't act (low score, or mitigation costs more).
Monitor | Watch for it; act if it materializes.

## Example
Risk Register — Worked Example
ID | Risk | Category | Likelihood | Impact | Score | Status | Mitigation | Owner | Updated
R1 | Deep-link preservation may have edge cases (session-scoped URLs) | Technical | Medium | Medium | 4 | Open | Spike in Week 1 to enumerate cases | Pat | 05-26
R2 | SSO vendor API rate-limits during testing | External | Medium | High | 6 | Open | Vendor support engaged; mock fallback for parallel work | Sam | 05-26
R3 | Browser back-button behavior may confuse users | Quality | Medium | Medium | 4 | Open | User testing in Week 7 | Riley | 05-26
R4 | On-call rotation Week 6 reduces capacity | Resource | High | Low | 3 | Mitigated | Confirmed coverage; Alex covering Week 6 | Sam | 05-20
R6 | Analytics event schema may conflict with existing | Technical | Low | Medium | 2 | Closed | Reviewed and aligned with analytics team | Jordan | 05-15