## Read Me
ShiftQuality Pro
RACI Matrix
Map who is Responsible, Accountable, Consulted, and Informed for every activity — so ownership is explicit and decisions don't stall.
The four roles:
• R — Responsible: does the work.
• A — Accountable: ultimately answerable. Exactly ONE per row.
• C — Consulted: gives two-way input before the work.
• I — Informed: told after the fact, one-way.
How to use it:
1. One row per activity, one column per person or role.
2. Put a letter in each cell. Exactly one A per row; keep R's few.
3. A cell can combine, e.g. 'A,R' (accountable and does the work).
4. Be sparing with C — too many stalls the work.
Variants: RASCI adds S (Supportive); RACI-VS adds V (Verifier) + S (Signatory).
ShiftQuality — real knowledge for builders. shiftquality.com

## Matrix
RACI Matrix
Activity | Person A | Person B | Person C | Person D | Person E | Person F
Define requirements
Design technical approach
Build features
Review and approve
Test
Communicate to stakeholders
Deploy
Verify
Support post-launch

## Example — Migration
RACI — Worked Example: Database Migration
Activity | Eng Lead | PM | SRE | Security | Support | Sponsor
Define scope | C | A,R | C | I | I | I
Design approach | A,R | C | C | C | I | I
Build migration tools | A,R | I | C | I | I | I
Security review | C | I | I | A,R | I | I
Customer comm plan | I | A,R | I | I | C | I
Execute migration | A,R | I | R | I | I | I
Verify post-migration | A,R | C | R | C | C | I
Go / no-go decision | C | C | C | C | I | A